## Sheet1
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TASK for ALGORITHM | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12
Complete project proposal | bar: 2022-10-17 to 2022-10-24
Search for feasible recognition model | bar: 2022-10-24 to 2022-11-07
Set up and manage image set | bar: 2022-10-31 to 2022-11-07
Adjust model performance | bar: 2022-10-31 to 2022-11-07
Compare four model performance | bar: 2022-11-14 to 2022-12-05
Write interim report | bar: 2022-11-28 to 2022-12-12
| Holiday | Holiday | Holiday | Holiday | Exam | Exam | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Holiday | Holiday | Holiday | Holiday
TASK for PROGRAM | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17
Look for other algorithm
Design the interface of website | bar: 2022-12-19 to 2023-01-23
Develop the framework of front end | bar: 2023-01-02 to 2023-02-06
Build the back end to connect dataset | bar: 2023-01-02 to 2023-02-13
develop the server structure to get and post | bar: 2023-01-02 to 2023-02-13
Implement the recognition algorithm | bar: 2023-02-13 to 2023-02-20
Write final diisertation | bar: 2023-02-27 to 2023-04-03
Work on the demo video | bar: 2023-03-06 to 2023-04-03